|  | (TITLE) |  |
| --- | --- | --- |
|  |  | by |  |  |
|  | (Your Name) |  |
|  |  | (Class) |  |  |
|  | (Name of Professor) |  |
|  | (University) |  |

BBQ fun is an e-commerce business, and its business activities and operational plan are affected by different external factors. Australian government demands different rules and regulations to be followed by e-commerce businesses such as registration of business name and obtaining its Australian Business Number (Business.gov.au, 2019). Policies and Procedures help in guiding the course of action and influence the decisions. In accordance with the operational plan of BBQ fun, the policies can be related to the roles and responsibilities of employees, maintaining the quality of goods and services and health and safety of their employees.

An operational plan provides the employees of an organization with clear pictures of their responsibilities according to the business objectives of the company (“Operations Planning and Management,” 2016). Basically, this plan will help BBQ fun in implementing the e-commerce strategy because it will identify tasks that will guide employees and will lead to the success of the strategy. The existing operational plan will be amended because it has some important elements of the operational plan but misses some of them such as timelines to complete one task and needs a process of monitoring progress. However, it uses the expert judgment to identify the risks that can occur in implementation.

To implement an e-commerce strategy successfully include different resources are required which include the website developers, warehousing for storage of goods, advertising and promotion, customer service department, equipment and office space.

Human resource requirement:

Website developers

Four Customer service people

Four warehouse workers

Training of existing employees

Six additional drivers

Physical resources requirement:

Office space reconfiguration

Engineering equipment and Trucks

Three forklifts

Action Plan:

| Action / Objective | Date | Person Responsible | Budget or Resource |
| --- | --- | --- | --- |
| Selection of Vendors for equipment and trucks | By 25th Jan | Manager Administration |  |
| Procurement of equipment | By 5th Feb | Manager Administration | For delivery Trucks: $300,000 Forklifts: $30000 |
| Office and Warehouse Reconfiguration | By 15th Feb | Manager Administration | $50000 |
| Recruitment of New employees | By 25th Feb | Manager Human Resource | $30000 |
| Training of Staff for Customer Service | By 5th Mar | Manager Human Resource | $24000 |
| Training of Store Managers | By 12th Mar | Manager Human Resource | $27000 |
| Communication among stakeholders | By 20th Mar | Operational Manager |  |

Balanced Scorecard:

Balanced Scorecard is a planning and management tool which helps an organization to communicate and measure and monitor the progress of its strategic targets. (“What is the Balanced Scorecard?” n.d.)

| KRA (key result area) | Target | KPI (key performance indicator) | Result |
| --- | --- | --- | --- |
| Supporting people to perform via training and performance management. | Numbers of injuries (Target = 0). Numbers of absentees (Target = <3% of total hours). Anti-discrimination complaints (Target=0). Lost Time Injury Frequency Rate (Target=2) Percentage completion of performance plans and performance management process. Numbers of coaching sessions completed. Numbers of operational-related training programs completed | Sales per representative Lead conversions Number of trained staff Employee Retention (Parmenter, 2015) | Increased employee performance due to training and management. |
| Increasing sales revenue. | General ledger accounts; financial statements: Revenue target = $11 million Profit target = $1,792,286 | Number of Orders Net Profit Margin | Higher profitability and business stability |
| Building a reputation for quality products and quality customer service: Raise organizational profile by 20%. Improve client satisfaction performance by 25%. | Percentage of brand recognition in sought-after categories in periodic customer surveys. Percentage of customers with positive view of organisational responsiveness, innovation, quality, ethics, safety. Number of customer complaints. Delivery times. Number of returned items. | Customer Retention Rate Customer Profitability Website Traffic Customer Feedbacks Customer Ratings | Positive word of mouth from customers. High customer retention rates and low customer churn. Less cost to acquire new customers |
| Engaging with customers through marketing, research, and personalised service. | Completion of market/marketing research. Completion of customer surveys. Completion of reports to identify marketing opportunities. | Customer engagement level Monthly New Customers Positive Reviews from Customers Customer Feedbacks | Increase in Customer Satisfaction Positive word of mouth from customers. |
| Reduce direct and indirect costs of operations | General ledger accounts; financial statements: wages cost of agent services consultancy fees Wastage and associated expenses. Expense target = $5,004,714 COGS target = $5,890,000 | Cost per Order Cost per customer conversion Cash flow statement Accounts Payable | Higher profitability and business stability High spending on marketing and other tasks to increase sales |

| Contingency Plan Company name: BBQfun Name of person developing the plan: Name: Position: Operational Manager |
| --- |
| Risks identified: 1. Risk of not being able to hire trained staff for customer service 2. Risk of Employee injuries while loading and unloading 3. Risk of loss of IP |
| Strategies/activities to minimise the risk | By when | By whom |
| Have clear procedures and standards designed to assess candidates before hiring | 1 month | HR |
| Choosing Experienced Candidates in the same fields of performance | 1 month | HR |
| Train employees to avoid any customer loss in future | 1 month | HR |
| Employee Trainings to Use equipment’s for loading and unloading | 2 month | HR |
| Health and Safety Rules and policies with documentation | 1 month | HR |
| Having employee insurance | 2 month | HR |
| Have contract with Web Developer | 1 month | Operations, IT |
| Have a data protection solution | 2 month | Operations, IT |
| Take Legal Help | 2 month | Operations, IT |

Proposal:

The physical and human resources identified are required to implement the e-commerce strategy of BBQ fun. Since the existing website is in need of improvement and the increased online sales also need warehousing space, new drivers and more trucks. Moreover, to fulfill the staffing needs of improved business, some new staff is required, and existing staff needs to be trained. All these resources will help in the better performance of business. The KPI’s are developed to see the increase in performance and are directed towards the organizational goals. By not implementing these resources organization can face failure to provide quality goods and services to customers which will decrease profitability. Company needs to meet the customer expectations by Australian law. This proposal is based on the company’s needs and the technical and business requirements of BBQ fun. The following is the break-down of cost for these resources:

| Costs: e-Commerce strategy (initial investment) |
| --- |
| Resources | Costs |
| Plant and equipment | Delivery trucks $50,000 x 6 = $300,000 Forklifts $10,000 x 3 = $30,000 |
| Promotional costs | $300,000 |
| Website developers | $100,000 |
| Staff training | Online customer service training $3,000 per staff member = $24,000 |
| Recruitment costs | $30,000 |
| Management change leadership training for store managers and team leaders | $3,000 each = 1 Brisbane store manager, 4 Brisbane team leaders, 1 Gold Coast store manager and 3 Gold Coast team leaders x $3,000 = $27,000 |
| Warehouse and office reconfiguration | $50,000 |
| Total | $861,000 |

Bibliography

Business.gov.au. (2019). Legal Essentials for doing business online. [online] Available at: https://www.business.gov.au/marketing/websites/legal-essentials-for-doing-business-online [Accessed 17 Jan. 2019].

Operations Planning and Management, 2016. . Schroeder Schroeder.

Parmenter, D., 2015. Key performance indicators: developing, implementing, and using winning KPIs. John Wiley & Sons.

What is the Balanced Scorecard? [WWW Document], n.d. URL https://www.balancedscorecard.org/BSC-Basics/About-the-Balanced-Scorecard (accessed 1.17.19).